## Slide 1: SDLC models Traditional and Agile
Software Development Life Cycle models
CONFIDENTIAL | © 2019 EPAM Systems, Inc.
Zoltan_Gal@epam.com

## Slide 2: Development models
Waterfall model
Need, wish, policy, law
User requirements
System requirements
Global design
Detailed design
Implementation
Testing

## Slide 3: Development models
Everything needs to be defined early.
Sequential flow control.
Hard to push feedback up.
Hardly supports iteration.
Not reactive to changes.
Still with us today.
Waterfall model

## Slide 4: Development models
V-model
Need, wish, policy, law
User requirements
System requirements
Global design
Detailed design
Implementation
Component test execution
Integration test execution
System test execution
Acceptance test execution
Operational system

## Slide 5: Development models
Splitting up.
Usually equal length phases.
First serves as a base, sets up further phases.
Early release.
Supports early and dynamic feedback.
Cost (early vs. total).
Prototyping.
RAD, RUP.
Agile.
Incremental/iterative models (general)

## Slide 6: Development models
Incremental/iterative models (general)
Phase 1
Define
Develop
Build
Test
Implement
Phase 2
Define
Develop
Build
Test
Implement
Phase 3
Define
Develop
Build
Test
Implement

## Slide 7: Development models
iterative models
Analysis and design
Coding
Testing
Planning
Requirements
Evaluation
Inintial planning
Deployment

## Slide 8: Development models
Hybrid incremental model
Analysis
Coding
Testing
Need, wish, policy, law
User requirements
System requirements
Integration test execution
System test execution
Acceptance test execution
WATERFALL
WATERFALL

## Slide 9: Development models
Rad - Rapid Application Development
Promotes rapid prototyping
First a prototype is created bases on planning and user design
The prototype can be re-done or changed any number of time, as necessary
The product itself is developed based on the prototype
The final cutover phase takes the product into production
Advantages
  Reduced development time
  Increases reusability
  Early customer feedback
  Minimal integration issues
Disadvantages
  Only systems that can be modularized can be built using RAD
  High dependency on modeling skills
  High cost of modeling

## Slide 10: Development models
Rad phases
Anaysis and quick design
Testing
Deployment
Demonstrate
Refine
Develop
Protoype lifecycle

## Slide 11: Development models
RUP – Rational Unified Process
Belongs to the incremental model family from Rational, a division of IBM.
It helps parallelization of the workforce, for better utilization, so it is useful for the large scale, like hundreds of developers.
Phases
  Inception – Determine resource needs.
  Elaboration – Architecture and further resource evaluation.
  Construction – Design, coding, testing, completing.
  Transition – Release, feedback, final updates.

## Slide 12: Development models
RUP – Rational Unified Process

## Slide 13: Development models
Spiral model

## Slide 14: Development models
Agile manifesto
We are uncovering better ways of developing software by doing it and helping others do it.
Through this work we have come to value:
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
https://agilemanifesto.org

## Slide 15: Development models
Agile
“Agile”, the word has been applied around 2001 for building software in a non-traditional way
Features:
  low ceremony (fewer procedures, documents)
  more effective resource usage
  focused on customer and changes
  rapid development and feedback
Customer Satisfaction
An approach to building software, in which the overall lifecycle is composed of several iterations in sequence
Each iteration is a self-contained mini-project composed of activities such as requirements analysis, design, programming, and test
The system grows incrementally

## Slide 16: Development models
The scrum method overview

## Slide 17: Development models
The scrum - roles
Everyone else (managers, user acceptance testers, architects)
A Pig and a Chicken are walking down the road.
  The Chicken says: "Hey Pig, I was thinking we should open a restaurant!„
  Pig replies: "Hm, maybe, what would we call it?"
  The Chicken responds: "How about 'ham-n-eggs’?”
  The Pig thinks for a moment and says: "No thanks. I'd be committed, but you'd only be involved."
PO, SM, development team
vs

## Slide 18: Development models
The scrum method overview
Artifacts
  Product Backlog
  Sprint Backlog
  Product Burn Down Chart
  Sprint Burn Down Chart
Daily Scrum Meeting
  What did you accomplish yesterday?
  What are your working on today?
  What impediments in your way?
Sprint Review
Sprint Retrospective Meeting
Time Boxing

## Slide 19: Development models
Kanban

## Slide 20: Development models
Pair programming – Two people work in tandem on the same problem. Rotating partners is advised.
Planning game – This is how most of the planning for the project takes place.
  Release planning – Where determinations are made regarding what is required for impending releases.
    Exploration phase – Story cards for the most valuable requirements.
    Commitment phase – Planning and commitments from the team.
    Steering phase – Adjust previous plans.
  Iteration planning – Follows the release planning.
    Exploration phase – Requirements are written down.
    Commitment phase – Tasks are assigned and scheduled.
    Steering phase – Upon development competition results are checked against the original cards.
Test-driven development – Tests are created first based on requirements, only then is code developed against them.
Whole team – Include customers and clients throughout the entire process and use everyone’s feedback.
Fine-scale feedback - Extreme Programming Best Practices – I.

## Slide 21: Development models
Continuous Integration
  All code is merged into one repository (Master).
  Integrations tests ensure stability.
  Early and frequent integration reveals integration issues at the earliest possible time.
  Releases can be assembled in a short time.
  Continuous Delivery is the next step.
Code refactoring
  Improve and redesign the structure of already existing code.
  Behavior should not be modified.
  Fixing naming conventions.
  Reducing repeated code to a method or function.
Small releases – Release frequently (per hour/day/week/iteration) to show the whole team the current status.
Continuous process - Extreme Programming Best Practices – II.

## Slide 22: Development models
Coding standards
  Set of best practices within the code itself, formatting and style
  Applies to everyone who contributes
  Promotes better understanding and readability
  Ensure continuity for future contributors
Collective code ownership – Everyone should be able to modify all (or at least multiple) parts of the code
Simple design
  If there is a choice between simple and complex, always choose the simplest
  This applies for components and code snippets as well
  KISS – Keep It Simple, Stupid
System metaphor
  Everyone in the team should understand the whole system at least on a high level
  An easy way to reach this is to have a metaphor to everything, and use it in the naming conventions
Shared Understanding - Extreme Programming Best Practices – III.

## Slide 23: Development models
Sustainable pace
  Promotes a healthy work-life balance
  No work outside of the normal working hours
  No overtimes, no “crunch time”
Programmer welfare Extreme Programming Best Practices – IV.

## Slide 24: Pessimistic and optimistic estimation

## Slide 25: Why do we estimate?
Why?
We always estimate, time, money, stopping distance, our chances to get a date with the desired boy/girl, and everything
We use these estimations for making decisions about
  Investing in something, or skipping it
  Deciding between multiple options
Who?
Estimations can be done solo, or in a group
Group estimations might include
  People who are to realize the task if it needs to be done
  Experts who have done it more times than us
  The 2nd party, as an observer, or to provide details
Difficulties?
Quite hard to estimate the unknown
Not easy to be pessimistic
Estimation time is always used up
Managers think of it as the Holy Writ
Not everything is estimated
Too many plans rely on estimates
People are not universal
Changes are often not re-estimated
The skeleton falls out too late
Failures do not trigger re-estimation
Wrong people do the estimates

## Slide 26: Popular estimation techniques
Planning Poker
Three Amigos / Triad
T-Shirt Sizes
Three-Point / PERT
And many more…

## Slide 27: Three-Point Estimation
It is also called PERT, as Program Evaluation and Review Technique
It provides three points (no sh*t, Sherlock)
  Pessimistic (b)
  Realistic (m)
  Optimistic (a)
Benefits
  Increased accuracy
  Risks are considered early
  Risks are shared early
Funky mathematics to go with it
Double-triangular distribution
  E = (a + 4m + b) / 6
  SD = (b − a) / 6
Triangular distribution
  E = (a + m + b) / 3

## Slide 28: Three-Point Estimation
A Cool Graph
For e.g.
If optimistic estimate to finish a module is 12 days, most likely is 16 days and pessimistic estimate is 18 days , the 3 point estimate is
(12 + 4 * 16 + 18)/6 = 15.67 and spread is (18-12)/6 = 1.
This in turn means 95 % probability is that module will finish by 13.67 to 17.67 days (+/- 2 days for 2 sigma level)
Also, if we go by 99% probability or 3 sigma , the spread is +/- 3 days of mean estimate…
For day to day projects, 95% confidence level is good. For mission critical projects, go for 99%. Also, since spread at 95% is +/-2 days or of 4 days, the risk is of 4/15.67 = 0.25 or 25%.
A boring sample of magic

## Slide 29: Pessimistic and Optimistic Estimation
The key is simplification
  Three points -> Two points
    Pessimistic (p)
    Optimistic (o)
  Fibonacci -> Man-days
    It might already be ready, and easily available (0, 0.5)
    We need to work on it (1, 2, 3, …)
  Simple mean (m) calculation
    m = (p + o) / 2
  Adding contingency (c) in one go
    c = 0.2 * m
  Finalize (f) by simply adding them together
    f = m + c
  You call this simple?!
    This has a lot of math still!
    Show me an example!

## Slide 30: Pessimistic and Optimistic Estimation example
Task | Summary | O | P | M | C | F
TMNT-0001 | Create test report for Sprint 23 | 3 | 5 | 4 | 1 | 5
TMNT-0002 | Review requirements for Sprint 24 | 4 | 7 | 5.5 | 1.4 | 6.9
TMNT-0003 | Reclaim Cybertron | 2 | 9 | 5.5 | 1.8 | 7.3
TMNT-0004 | Expand smoke suite with Sprint 22 items | 5 | 10 | 7.5 | 2 | 9.5
TMNT-0005 | Test design for the multiple document view feature | 2 | 3 | 2.5 | 0.6 | 3.1
TMNT-0006 | Avenge the death of Alex J. Murphy | 7 | 11 | 9 | 2.2 | 11.2
TMNT-0007 | Create ramp-up plan for new the new team member | 3 | 7 | 5 | 1.4 | 6.4
TMNT-0008 | Bring swift death to the enemies of Mankind | 1 | 4 | 2.5 | 0.8 | 3.3
TMNT-0009 | Update test set user info for the new environment | 5 | 7 | 6 | 1.4 | 7.4
SUM |  | 32 | 63 | 47.5 | 12.6 | 60.1

## Slide 31: T-Shirt Size Technique
It’s one of the Agile Story Point Estimation Techniques.
It’s a relative estimation technique.
Based on the US t-shirt sizes: Small (S), Medium (M), Large (L) and Extra Large (XL) and so on.
Smaller than XS = a Task, Larger than XL = an Epic.
Allows a more dynamic approach.
PO explains, then questions follow:
  Design-related: e.g. Do we have to learn new things before starting the design/HTML/jQuery etc?
  Coding-related: e.g. Do we have any code class library ready or we have to write it from the scratch?
  Testing-related: e.g. Any specific setup required for testing?
After everyone showing their chosen t-shirt size, the team might need to debate, and redo the exercise.
  One of the smallest t-shirt size showers should explain why.
  One of the largest t-shirt size showers should explain why.
After all items are done, place them in their respective buckets.

## Slide 32: T-Shirt Size Technique

## Slide 33: Useful AGILE links
Scrum Alliance - http://www.scrumalliance.com
Mountain Goat Software - http://www.mountaingoatsoftware.com
Agile Alliance - http://agilealliance.com
VersionOne - http://www.versionone.com/Agile101/
EPAM Agile Professional Development Suite - https://www.epam.com/our-work/brochures/agile-professional-development-suite

## Slide 34: “To question is to doubt” Imperial thought for the day
Thank you For your attention!
Zoltan_Gal@EPAM.com